## Overview
Crop Disease Detection Toolbox — Version 2 Roadmap
12-month plan ¦ Cycle start: August 2026 ¦ Cycle end: July 2027 ¦ Prepared: July 15, 2026
Phase | Timeframe | Duration | Primary Owner | Objective | Exit Criteria (moves to next phase) | Status
1. Model Refinement | Aug – Sep 2026 | 2 months | ML Engineer | Improve SE-FPN / YOLO26 / classifier accuracy and robustness beyond v1 baseline; expand and clean the Ghana Crop Disease Challenge dataset; reduce false positives on non-crop (OOD) images. | Refined checkpoints for classifier, YOLO26 and SE-FPN outperform v1 final_output on held-out test set; mAP and classifier accuracy targets agreed with team are met. | Not Started
2. Internal Benchmarking | Oct 2026 | 1 month | ML Engineer / QA Engineer | Formally benchmark all candidate models (classifier, YOLO26, Faster RCNN v2, SE-FPN) on accuracy, latency, model size and on-device performance to select the production pipeline. | Benchmark report signed off; one detector (YOLO26 or SE-FPN) and the classifier formally selected as the v2 production pipeline with documented rationale. | Not Started
3. Internal Testing (QA) | Nov 2026 | 1 month | QA Engineer | Stress-test the selected pipeline against edge cases: poor lighting, blur, mixed crops, non-crop leaves, low-end devices, and offline conditions. | Internal test plan executed with no critical/blocking defects open; known limitations documented in docs/. | Not Started
4. Application Refinement | Dec 2026 – Jan 2027 | 2 months | Mobile App Developer | Build/refine the native Android/iOS app around the exported .ptl / .pte mobile models: on-device inference, camera capture flow, results UI, offline mode, crop/disease reference library. | Functional app build (Android + iOS) running on-device inference end-to-end, passes internal QA smoke tests. | Not Started
5. Application & Model Deployment (Internal) | Feb 2027 | 1 month | Mobile App Developer / Project Lead | Package and deploy the app internally (TestFlight / internal Android track), finalize model versioning and update mechanism, prepare app store listings. | App installable by internal stakeholders and field team; versioned model artifacts and rollback plan in place. | Not Started
6. Personnel Training | Mar 2027 | 1 month | Field/Training Coordinator | Train extension officers and field agents (Ashanti Region) on app usage, image capture technique, interpreting results, and escalation/feedback reporting. | All assigned field personnel complete training and pass a hands-on usage checkout; training materials finalized. | Not Started
7. Beta Testing (Ashanti Pilot) | Apr – May 2027 | 2 months | Field/Training Coordinator / QA Engineer | Run supervised pilot in the Ashanti Region with trained field personnel and real farmers; collect usage data, misclassifications, crash reports and farmer feedback. | Target number of pilot users/sessions reached; feedback and error logs consolidated into a findings report. | Not Started
8. Beta Refinement | Jun 2027 | 1 month | ML Engineer / Mobile App Developer | Retrain/fine-tune models on beta-collected data and images; fix app bugs and UX issues surfaced during the pilot. | Updated model + app build addresses top issues from the beta findings report; regression-tested by QA. | Not Started
9. Production Deployment (Nationwide) | Jul 2027 | 1 month | Project Lead / Mobile App Developer | Publish to app stores, roll out nationwide, stand up monitoring/analytics and a support channel for ongoing feedback. | App live on Google Play / App Store nationwide; monitoring dashboard active; v3 backlog opened from launch feedback. | Not Started
Visual Timeline
Phase | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27
1. Model Refinement
2. Internal Benchmarking
3. Internal Testing (QA)
4. Application Refinement
5. Application & Model Deployment (Internal)
6. Personnel Training
7. Beta Testing (Ashanti Pilot)
8. Beta Refinement
9. Production Deployment (Nationwide)

## Monthly Plan
Version 2 — Monthly Execution Plan
One row per active workstream per month. Update Status as work progresses.
Month # | Month | Phase | Workstream | Owner (Role) | Key Activities | Deliverables | Success Metric / Exit Criteria | Dependencies | Status
1 | Aug-2026 | 1. Model Refinement | ML Engineering | ML Engineer | Audit v1 model errors (classifier + SE-FPN + YOLO26); expand/clean dataset (relabel noisy boxes, add hard negatives); begin hyperparameter and augmentation refinement. | Error analysis report; cleaned dataset v2; updated training configs | Root-cause list of top v1 failure modes documented | v1 final_output checkpoints and figures; docs/07_dataset.md | Not Started
1 | Aug-2026 | 1. Model Refinement | Project Coordination | Project Lead | Kick off v2 cycle: confirm team roles, finalize this roadmap, set up tracking board, confirm Ashanti pilot logistics contact. | v2 kickoff doc; tracking board set up | Team aligned on roadmap, roles and success metrics | Team availability confirmed | Not Started
2 | Sep-2026 | 1. Model Refinement | ML Engineering | ML Engineer | Complete refined training runs (classifier, SE-FPN, YOLO26); re-run ablations if needed; freeze candidate checkpoints for benchmarking. | Refined checkpoints (best.pth / best.pt) for all pipelines; updated metrics_history.json | Refined models beat v1 baseline mAP/accuracy on validation split | Row above (dataset v2, configs) | Not Started
2 | Sep-2026 | 1. Model Refinement | QA Prep | QA Engineer | Draft internal test plan and edge-case image set (poor lighting, blur, mixed/occluded leaves, non-crop images) ahead of benchmarking and testing phases. | Draft internal test plan; curated edge-case test image set | Test plan reviewed and approved by ML Engineer | None | Not Started
3 | Oct-2026 | 2. Internal Benchmarking | ML Engineering | ML Engineer | Benchmark classifier, YOLO26 and SE-FPN on accuracy (mAP/F1), inference latency, and exported model size (.ptl/.pte/.onnx) on representative Android/iOS hardware. | Benchmark report comparing all candidate models | Clear winner(s) identified against agreed accuracy/latency/size thresholds | Refined checkpoints from Month 2; export.ipynb pipeline | Not Started
3 | Oct-2026 | 2. Internal Benchmarking | QA Support | QA Engineer | Validate benchmark methodology; independently re-run key benchmark numbers to confirm reproducibility. | Benchmark sign-off checklist | Numbers reproduced independently within acceptable variance | ML benchmark report (draft) | Not Started
3 | Oct-2026 | 2. Internal Benchmarking | Project Coordination | Project Lead | Review benchmark results with team; formally select the v2 production pipeline (detector + classifier) and document rationale. | Pipeline selection decision record | Decision documented and communicated to app team | Benchmark report | Not Started
4 | Nov-2026 | 3. Internal Testing (QA) | QA Engineering | QA Engineer | Execute the internal test plan against the selected pipeline: edge cases, OOD/non-crop rejection, device compatibility, offline behaviour. | Test execution log; defect list with severity | Zero critical/blocking defects remain open | Selected pipeline from Month 3; test plan from Month 2 | Not Started
4 | Nov-2026 | 3. Internal Testing (QA) | ML Engineering | ML Engineer | Fix model-side defects found in testing (threshold tuning, additional hard negatives, misclassification patterns). | Patched checkpoints; updated confidence thresholds | Re-test of fixed defects passes | QA defect list | Not Started
5 | Dec-2026 | 4. Application Refinement | Mobile App Development | Mobile App Developer | Build core Android/iOS app: camera capture flow, on-device inference using .ptl/.pte exports, results screen with disease info and confidence scores. | Working app build (alpha) with end-to-end on-device inference | Alpha build runs the full capture-to-diagnosis flow without crashing | Selected pipeline + mobile exports from export.ipynb | Not Started
5 | Dec-2026 | 4. Application Refinement | ML Engineering | ML Engineer | Support mobile integration: verify exported model outputs match Python inference, tune thresholds for on-device use, package model_metadata.yaml for app team. | Verified export parity report | On-device predictions match reference Python predictions within tolerance | App alpha build | Not Started
6 | Jan-2027 | 4. Application Refinement | Mobile App Development | Mobile App Developer | Add offline mode, crop/disease reference library, feedback/report-issue feature, basic analytics hooks, localisation (English + local language groundwork). | Feature-complete beta build (Android + iOS) | All planned v2 app features implemented and demoed to team | Alpha build feedback | Not Started
6 | Jan-2027 | 4. Application Refinement | QA Engineering | QA Engineer | Run app-level QA: usability testing, device/OS matrix testing, offline/low-connectivity testing, crash and performance testing. | App QA report | No critical app defects open; performance acceptable on target low/mid-range devices | Feature-complete beta build | Not Started
7 | Feb-2027 | 5. Application & Model Deployment (Internal) | Mobile App Development | Mobile App Developer | Finalize app signing, versioning and update mechanism; publish to internal distribution (TestFlight / internal Android track); prepare app store listing drafts. | Internally distributed release build; draft store listings | App installable by all internal stakeholders and field team via internal channel | QA sign-off from Month 6 | Not Started
7 | Feb-2027 | 5. Application & Model Deployment (Internal) | ML Engineering | ML Engineer | Finalize model versioning scheme and rollback plan; document model_metadata.yaml and update process for future retrains. | Model versioning/rollback plan | Rollback tested successfully at least once | Feature-complete beta build | Not Started
7 | Feb-2027 | 5. Application & Model Deployment (Internal) | Project Coordination | Project Lead | Confirm Ashanti Region pilot plan: site/farmer recruitment, field personnel list, device provisioning, timeline with local extension office. | Ashanti pilot logistics plan | Pilot sites and field personnel confirmed | None | Not Started
8 | Mar-2027 | 6. Personnel Training | Field Training | Field/Training Coordinator | Deliver hands-on training to extension officers/field agents on app usage, correct image capture, interpreting results, and reporting feedback/issues. | Training sessions delivered; training manual/quick-reference guide | 100% of assigned field personnel complete training and pass usage checkout | Internal release build from Month 7 | Not Started
8 | Mar-2027 | 6. Personnel Training | Mobile App Development | Mobile App Developer | Provide training support materials (in-app tutorial/onboarding flow); fix any usability issues surfaced during training sessions. | In-app onboarding/tutorial flow; hotfix build if needed | Trainees can complete a full diagnosis flow unassisted after onboarding | Training sessions | Not Started
9 | Apr-2027 | 7. Beta Testing (Ashanti Pilot) | Field Pilot | Field/Training Coordinator | Launch supervised pilot with trained field personnel and farmers across pilot sites in Ashanti Region; begin structured data and feedback collection. | Pilot launched; weekly usage/feedback logs | Target number of active pilot users/sessions reached for Month 1 of pilot | Trained personnel from Month 8 | Not Started
9 | Apr-2027 | 7. Beta Testing (Ashanti Pilot) | QA / Monitoring | QA Engineer | Monitor app stability, crash reports and misclassification reports from the field; triage issues by severity. | Weekly QA monitoring report | Critical issues triaged within 48 hours | Pilot launch | Not Started
10 | May-2027 | 7. Beta Testing (Ashanti Pilot) | Field Pilot | Field/Training Coordinator | Continue pilot; conduct farmer/field-agent interviews and satisfaction surveys; collect misdiagnosis examples for retraining. | Farmer feedback survey results; misdiagnosis image set | Pilot completes with statistically usable feedback sample | Month 9 pilot data | Not Started
10 | May-2027 | 7. Beta Testing (Ashanti Pilot) | Project Coordination | Project Lead | Consolidate all beta findings (usage data, bugs, model errors, farmer feedback) into a single findings report with prioritized issues. | Beta findings report | Findings report reviewed and prioritized with team | All pilot data | Not Started
11 | Jun-2027 | 8. Beta Refinement | ML Engineering | ML Engineer | Fine-tune/retrain models using beta-collected images and misdiagnosis cases; re-run benchmarking on updated checkpoints. | Beta-refined model checkpoints | Refined models show measurable improvement on beta-collected test set | Beta findings report | Not Started
11 | Jun-2027 | 8. Beta Refinement | Mobile App Development | Mobile App Developer | Fix top app bugs and UX issues from pilot feedback; integrate refined model exports; prepare release-candidate build. | Release-candidate app build | Top-priority beta issues closed and verified | Beta findings report; refined models | Not Started
11 | Jun-2027 | 8. Beta Refinement | QA Engineering | QA Engineer | Regression-test the release-candidate build against the full internal test plan plus new beta-derived test cases. | Regression test report; go/no-go recommendation | Release candidate passes regression suite with zero critical defects | Release-candidate build | Not Started
12 | Jul-2027 | 9. Production Deployment (Nationwide) | Mobile App Development | Mobile App Developer | Submit and publish app to Google Play and Apple App Store; finalize production listing, screenshots and support links. | App live on Google Play / App Store | App approved and publicly available nationwide | Go/no-go from Month 11 | Not Started
12 | Jul-2027 | 9. Production Deployment (Nationwide) | Operations / Monitoring | ML Engineer / QA Engineer | Stand up production monitoring/analytics (usage, crash, model confidence trends) and a user support/feedback channel. | Monitoring dashboard; support channel live | Monitoring active from day 1 of nationwide launch | Published app | Not Started
12 | Jul-2027 | 9. Production Deployment (Nationwide) | Project Coordination | Project Lead | Run nationwide launch communications with extension services/partners; open the v3 backlog from launch feedback and lessons learned. | Launch communication; v3 backlog; end-of-cycle retrospective | Retrospective completed; v3 backlog has at least an initial prioritized list | Published app; monitoring data | Not Started

## Team & Roles
Team & Roles
Small team (2–5 people). Roles can be combined for smaller teams.
Role | Core Responsibilities | Primary Phases | Time Commitment | Notes
Project Lead | Overall v2 coordination, stakeholder communication, Ashanti pilot logistics, go/no-go decisions | 1, 2, 5, 7, 9 | Part-time throughout; heavier in Phases 5, 7, 9 | Can double as ML Engineer or Mobile App Developer in a 2–3 person team
ML Engineer | Model refinement, benchmarking, retraining from beta data, mobile export verification | 1, 2, 3, 4, 8, 9 | Full-time Phases 1–2; part-time elsewhere | Owns train_classifier.py, train.py, train_final.py, export.ipynb
Mobile App Developer | Native Android/iOS app build, on-device inference integration, app store deployment | 4, 5, 6, 8, 9 | Full-time Phases 4–5 | Consumes .ptl/.pte exports from outputs/*/models/
QA Engineer | Test planning, internal QA, app QA, regression testing, beta monitoring | 2, 3, 4, 7, 8 | Full-time Phase 3; part-time elsewhere | Owns internal test plan and defect tracking
Field/Training Coordinator | Personnel training design and delivery, Ashanti pilot management, farmer feedback collection | 6, 7 | Full-time Phases 6–7 | Local presence in Ashanti Region required during pilot

## Risks & Assumptions
Risks & Assumptions
Review and update monthly alongside the execution plan.
Key Assumptions
- Team size is small (2–5 people); roles in the Team & Roles sheet may be combined across fewer individuals.
- v2 ships as a native Android/iOS app using the existing .ptl (TorchScript mobile) and .pte (ExecuTorch) exports already produced by export.ipynb.
- Beta/pilot testing runs in the Ashanti Region only; production deployment target is nationwide (Ghana).
- Dataset remains the Ghana Crop Disease Challenge v2 (Roboflow, CC BY 4.0), expanded with beta-collected field images in Phase 8.
- Plan timeline starts August 2026 (next full month after this plan was drafted, July 15, 2026) and runs 12 months to July 2027.
Risk Register
Risk | Phase(s) Affected | Likelihood | Impact | Mitigation
Refined model does not clearly outperform v1 baseline | 1, 2 | Medium | High | Set explicit go/no-go accuracy thresholds before starting; keep v1 SE-FPN as fallback pipeline
On-device inference latency/model size too high for low/mid-range Android devices common in target region | 2, 4 | Medium | High | Benchmark on representative low/mid-range hardware early in Phase 2; consider quantization
Limited/unreliable connectivity in Ashanti pilot sites affects app usage or data upload | 7 | High | Medium | Offline-first design finalized in Phase 4; batch-sync feedback/logs when connectivity returns
Field personnel availability or training turnout lower than planned | 6, 7 | Medium | Medium | Confirm personnel list and schedules with extension office one month ahead (Phase 5)
Small team bandwidth causes phase overlap/slippage | All | Medium | Medium | Monthly Plan sheet tracks status per workstream; Project Lead reviews monthly and re-sequences if needed
App store review delays nationwide launch | 9 | Low | Medium | Submit for review 2–3 weeks ahead of planned Phase 9 launch date
Beta findings require larger-than-expected model retraining effort | 8 | Medium | Medium | Prioritize top issues from findings report; scope Phase 8 retraining to highest-impact fixes only